## 1.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 1: URGENT & EMERGENCY CARE |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
• Increased clinical assessment of calls to NHS 111 & CAS • Promote the use of NHS 111 as a primary route into all urgent care services - maximise the use of booked time slots in A&E • Delivery of 4 hour A&E standard (or new targets arising from the Clinical Review of Standards) • maximise the utilisation of direct referral from NHS 111 to other hospital services (including SDEC and specialty hot clinics) and implement referral pathways from NHS 111 to urgent community and mental health services • Enhance Same Day Emergency Care including acute frailty services, increasing the proportion patients discharged on the day of attendance and avoiding unneccessary hospital admission. • Improved patient flow and reduce length of stay • Rollout of the 2-hour crisis community health response at home (8am-8pm, seven days a week) by April 2022 |  |  |  |  | Highest quality governance |  |  | If partners locally and across the ICS do not engage constructively together, to develop a model for urgent care at a South Yorkshire and Bassetlaw and Barnsley level, in line with best practice and national guidance there is a risk that urgent care services are unable to meet the growing demand, constitution standards for urgent care are not achieved and the quality of patient care is negatively impacted.
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
E2 - Ensuring the use of NHS111 as the primary route to access urgent care and the timely admission of patients to hospital who require it from emergency departments
Committee Providing Assurance |  |  | FPC | Executive Lead |  |  | JW | Clinical Lead |  |  |  | JH & MS
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 12 | [5 empty] | Rationale: Likelihood currently judged to be 'possible' given current pressures and challenges across the urgent care system and the developing nature of plans to deliver outcomes of the national urgent care review. Consequence is judged as major due to the potential impact on patient care.
Current | 4 | 4 | 16
Appetite | 3 | 4 | 12
Approach | Treat
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Operational planning process completed for 2021/22 in line with the NHS Planning Guidance. All activity plans are in line with national expectations for increased activity levels back toward those in 2019/20, reflecting local restrictions and transformation work to redesign services. Plans at provider and commissioner level are aligned to reflect the total Barnsley population. Planning has commenced for 2022/23 in line with NHS 2022/23 Priorities and Operational Planning Guidance. | [5 empty] | CCG worked with the NHSE and the SYB ICS to formulate a ICS level activity plan. Plan was submitted to NHSE in line with required deadlines. Activity levels are monitored on an ongoing basis to monitor delivery against submitted plans. | [5 empty] | Ongoing
Barnsley UEC Delivery Board meets monthly, with representation from the CCG, to ensure oversight of performance and planning for urgent care locally and ensure delivery of urgent care standards including local system wide planning for winter and other seasonal pressures. | [5 empty] | CCG GB members (x2) and Chief Operating Officer represent the CCG as members of the local delivery board. UEC Delivery Board Performance Dashboard is in place enabling all key performance and activity information from across partners to be reviewed by the Board and for actions to be agreed to address any areas of concern. UEC Delivery Board Priorities have been agreed as: A&E Front Door & 111 First, Enahancement and expansion of SDEC, Reducing avoidable admissions and readmissions. Revised UEC Board Plan has been developed in line with Planning Guidance and other NHSE Guidance on the transformation of urgent and emergency care, including implementation of new standards. Barnsley Flu Plan is in place and agreed by partners Barnsley are engaged in a SYB Improving Urgent and Emergency Care programme being supported by NHSE national improvment teams to support further imptovement of UEC services. | [5 empty] | Ongoing
Urgent and Emergency Care Steering Board is in place as the UEC Programme Board of the South Yorkshire and Bassetlaw Integrated Care System. Representation in place for the UEC Delivery Board partners on the Steering Group and Commissioner Reference Group. | [5 empty] | Barnsley UEC Delivery Board are represented by Barnsley CCG COO and Barnsley Hospital Director of Operations)ensuring Barnsley place is contributing to system developments. SYB UEC Steering Board has agreed priorities which all places are signed up to deliver locally. Oversight by the SYB Steering Board and locally through the UEC Delivery Board. | [5 empty] | Ongoing
The CCG is working with partners to improve the out of hospital service offer and ensure that more people are able to be cared for and treated at home or in a community setting without the need for an hospital attendance or admission. | [5 empty] | Community Services specification is in place for integrated community and primary care services working as part of the PCN/Neighbourhood arrangements with a focus on providing proactive care at home or in a community setting and supporting people to be better able to manage their own conditions. Integrated Care Partnership Group principles have been agreed and partnership plans developed to support the overall vision for 'left shift' Barnsley Place plan has been agreed by the Barnsley Intergrated Care Partnership with clear priorities for out of hospital services which are being taken forward through the Care Closer to Home Board. | [5 empty] | In progress
Urgent Care Services are in place and continuing to deliver improvements to already strong performance and enabling the ongoing delivery of planning priorities.An Integrated extended hours and out of hours primary care services (IHEART 365) is in place with contracts for both elements of service delivered by Barnsley Healthcare Federation. | [5 empty] | IUC/CAS is in place, increasing access to clinical advice and with the ability to book directly into primary care appointments for patients with a primary care need A&E waiting time performance is consistently high, length of stay low and flow good through and out of hospital ensuring low levels of DTOC Ambulatory Care/SDEC pathways are in place including Clinical Decsion Unit, Acute Frailty Unit, Ambulatory Medical Assessment Clinic, Surgical Assessment Unit and Childrens Assessment Unit - These areas are subject to ongoing work to improve access and enhance the service offer to avoid attendance at ED where possible | [5 empty] | Ongoing
Performance reports to Finance and Performance Committee and Governing Body on the delivery of constitution standards and CCG Improvement and Assessment Framework. Twice yearly assurance reports provided to Governing Body. | [5 empty] | Monthly reporting through the Integrated Performance Report to Finance and Performance Committee and bi-monthly to Governing Body | [5 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
The continued and ongoing impact of COVID19 has impacted upon the delivery of plans and the capacity of UEC services within Barnsley and therfore consitution standards are not being achieved, patients are often waiting longer than expected for Ambulance and A&E and also to be admitted to hospital where this is required.
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
RR 18/04: If the health and care system in Barnsley is not able to commission and deliver out of hospital urgent care services which have sufficient capacity and are effective in supporting patients in the community to avoid the need for hospital attendance or non-elective admission there is a risk that non- elective activity will exceed planned levels potentially leading to (a) failure to achieve NHS Constitution targets (with associated reputational damage, and (b) contractual over performance resulting in financial pressure for the CCG | [6 empty] | Regular review of activity data as part of contract and performance management and monitoring arrangements. Other data reviewed and analysed to identify new opportunities to reduce non elective activity e.g. NHS Rightcare Packs, Dr Foster data etc. The UEC Delivery Board is overseeing work to develop appropriate services to ensure that patients are able to access appropriate care and support outside of hospital, or in a different way in hospital utilising ambulatory care pathways and implementing a model to incorporate '111 First' CCG commissioned Out of Hospital Services have been remodeled as part of the Neighbourhood Team mobilisation and includes PCN/Neighbourhood developments.
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 16 | 16
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 2.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 2: PRIMARY CARE |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
Delivery of the Long Term Plan Delivery of the Primary Care Network Contract DES to support the continued development of the Primary Care Network and sustainable primary care medical services. Support the reset of core GMS/PMS/APMS contract delivery across primary care Support the embedding of new ways of working learned from the pandemic Deliver investment into Primary Care and improve health inequalities via the Practice Delivery Agreement (PDA). The PDA for 2021-22 has schemes for practice delivery that supports the NHSE/I Planning Guidance and also plans in place to support using the Covid Expansion Funds (£120m). Support practice quality improvement and CQC rating by use of the Quality Dashboard and regular meeting to support action plan delivery for those practices having domains that "require improvement" Ensure recruitment/retention/development of the clinical and non-clinical workforce Work with the PCN to maximise recruitment under the Additional Roles Reimbursement Scheme and take action to support them to meet recruitment plans Support the recruitment and retention of extra doctors working in general practice. Improve access particularly during the working week with more bookable appointments at evenings and weekends. Improve access by offering online booking, online consultation, total triage and other digital options and to focus on supporting improvements in practices with long waits for routine appointments Provide CCG support to implement the current DES Service Specifications and to support preparation for the remaining Service Specification to be delivered from Oct 2021 Meet 2021/22 trajectories set out in the Network Contract DES and support planning to achieve the KPIs. Improve infrastructure, digital capability, digital literacy and inclusion. Deliver delegated Primary Care functions to be confirmed via mandated internal audit reviews |  |  |  |  | Highest quality governance |  |  | There is a risk to the delivery of Primary Care priorities if the following threat(s) are not successfully managed and mitigated by the CCG: - Engagement with primary care providers and workforce - Workforce and capacity shortage, recruitment and retention - Under development of opportunities of primary care at scale, including new models of care - Primary Care Network and Neighbourhoods do not mature and develop to a level that supports the integrated delivery of Primary Care at place - BHF do not develop as a strong partner to support Primary Care at Scale - Not having quality monitoring arrangements embedded in practices - Inadequate investment in primary care - Independent contractor status of General Practice - Preparations for moving to ICS as a statutory body impacts on capacity to deliver transformation
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
D1 - Restoring and increasing access to primary care services
Committee Providing Assurance |  |  | PCCC | Executive Lead |  |  | JW / JF | Clinical Lead |  |  |  | MG
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 12 | [5 empty] | Rationale: Likelihood has been scored at 3 (possible) but will be kept under review. Consequence has been scored at 4 (major) because there is a risk of significant variations in quality of and access to care for patients if the priorities are not delivered.
Current | 3 | 4 | 12
Appetite | 3 | 4 | 12
Approach | TOLERATE
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
All practices are required to complete the National Workforce Data Return. ARRs roles identified in the PCN workforce plan and recruitment plans in place. Monitoring in place. | [5 empty] | National database regularly updated to show workforce National PCN Dashboard developed and evolving CCG to monitor recruitment by PCN | [5 empty] | Ongoing
Additional investment above core contracts through PDA delivers £4.2 to Barnsley practices to improve sustainability and attract workforce to the Barnsley area | [5 empty] | Ongoing monitoring of PDA (contractual / QIPP aspects via FPC, outcomes via PCCC). In line with national temporary contract changes to support GP practices to prioritise vaccination the CCG PCCC agreed to pay the PDA in full for Q3 and Q4. | [5 empty] | Ongoing
Optimum use of BEST sessions A contract is in place with BHF for the BEST programme which enables the CCG to support the programme | [5 empty] | BEST programme and Programme co-ordination being led by BHF with input from CCG Medical Director Contract management meetings in place to assess and reporting via PCCC | [5 empty] | Ongoing
Established a Primary care Strategy Group and delivery Group to support delivery of the primary Care Transformation programme. Development of Neighbourhood working within each of the 6 Neighbourhoods supported by the PCN and CCG. Bi-monthly PCN meetings established for all practices in the PCN. The 3 service specification from the Network Contract DES are now being undertaken by practices across each Neighbourhood. Work with the PCN to prepare for the next Service Specifications Work with the PCN regardin tackling health inequalites which have been further impacted by Covid. PCN Manager meetings set up with the CCG PC Team to support the Long Term Plan and DES delivery. | [5 empty] | Primary Care Strategy Group working as a sub-group of PCCC Primary Care Delivery Group working to deliver the transformation programme Neighbourhood Networks have been agreed with the support of a single Primary Care Network facilitated by the GP Federation. This supports the transition and development of the PCN via the Neighbourhoods to deliver the primary care elements of the NHS Long Term Plan and Network Contract DES. Meetings are set for the year to ensure that the PCNs are able to meet regularly. | [5 empty] | Ongoing
BHF - Existence of strong federation supports Primary Care at Scale | [5 empty] | BHF contract monitoring, oversight by PCCC | [5 empty] | Ongoing
Practices increasingly engaging with Community, voluntary and social care providers Personalisation/Social Prescribing - My Best Life is a successful programme supporting the people of Barnsley to work towards self care and the PCN are now delivering a young peoples Social Prescribing service. Work towards joining the services together as directed in the Network Contract DES. Collaboration to deliver primary care transformation and service delivery | [5 empty] | Personalisation and Social Prescribing are key elements in the Long Term Plan. Care Coordiantios, Health and Wellbeing Coaches are in place to support people with self care. Primary Care Strategy Group working as a sub-group of PCCC Primary Care Delivery Group working to deliver the transformation programme | [5 empty] | Ongoing
Engagement and consultation with Primary Care (Membership Council, Practice Managers etc.) | [5 empty] | NHS England 360 Stakeholder Survey results shared with stakeholders and published on the CCG website. Ensuring BCCG stakeholders have a high level of satisfaction with the CCG's leadership & engagement. | [5 empty] | Ongoing
SYB ICS has a workforce hub established, regular PC workforce meetings established which enables PC in Barnsley to collaborate with other CCGs, HEE, providers and Universities. | [5 empty] | BCCG is represented on all workforce groups. Reporting is via PCCC for Primary care. | [5 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
MAY 21 - PCN CD/Management meetings do not have regular input from CCG PC Commissioner therefore not able to support the development and maturing of the PCN nor have an effective comms route for sharing ICS/Regional and emergent information to support the Network Contract DES delivery. | [6 empty] | The PC Team and PCN CDs work with member practices to address any gaps/ variance and to develop a workforce plan going forward supported by the Additional Role Recruitment via the Network Contract DES. The rolling recruitment and inclusion of new roles each year supports the PCN service delivery. PCN workforce plan completed and submitted Nov 21 in line with guidelines to maximise use of ARRS Working closely with BHF to ensure the PCN maximise the recruitment opportunity for Barnsley. Ongoing linked to above - recuitment to all roles currently in line with plan. Practices encouraged to look at skill mix with innovative recruitment. The Primary Care Network and underpinning 6 Neighbourhood Networks are established and working on all elements of the Network Contract DES and Long Term Plan. The PC Team work closely with the PCN Managers to ensure delivery is on track. NHS England 360 Assurance audit in progress to provide NHS England with assurance of robust Primary Care processes. New topics are identified each year and the Head of Primary Care works with 360 to complete each plan. Requested the the CCG Medical Director be involved with the planning of the BEST sessions as per contract - Established process in place. 2021-22 PDA includes reference to work required for PC from the Planning Guidance.
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 3.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 3.1: CANCER |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
• Preventing cancer incidence • Reduced Inequalities especially those diagnosed at emergency admission. • Improved cancer diagnosed rates at stage 1 or 2 • Early Diagnosis - Implement rapid assessment and diagnosis pathways for all tumour sites • Improve care and treatment - embed new cancer waiting times system • Improve Patient Experience along pathways and LWBAC • Increasing Positive Experience at EOL by increasing early identification and reducing 3 or more admissions in last 3 months of life • Deliver Survivorship Program (LWABC) including recovery package and stratified pathways • Commissioning for Value adopted if appropriate • Achieve 10 waiting time standards including the 62 day referral-to-treatment cancer standard and 28 day faster diagnosis standard and pre-covid position. |  |  |  |  | Highest quality governance |  | ü | 1. Risk to delivery of the 62 day wait NHS Constitution standard if clear pathways from cancer diagnosis to treatment are not developed; capacity in place to meet the demand and services are able to respond to the impact of Covid restrictions on delivery of the Cancer Waiting Times. 2. Risk to delivery of early diagnosis if:(a) the CCG does not work in partnership with BMBC and PHE to promote to the people of Barnsley the national screening programme (b) Practices do not consistently apply NICE guidance for cancer diagnosis and referral and deliver the PCN DES via clinical systems and project delivery plan . 3. Risk that, if the CCG does not have a clear local strategy for delivering cancer priorities and performance, Barnsley people morbidity and mortality from cancer will be impacted negatively for people at risk of cancer; Living With and Beyond Cancer (LWABC) and improving 62 day target and delivering 10 CWT standards . 4. Risk that the incidence of cancer is not reduced, and of poorer outcomes post treatment, if steps to promote healthy lifestyles for Barnsley people are not successful.
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
C2 - Restore full operation of all cancer services
Committee providing assurance |  |  | FPC | Executive Lead |  |  | JW | Clinical Lead |  |  |  | Dr H Kadarsha
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 12 | [5 empty] | RATIONALE: Likelihood has been scored at 5 due to performance issues because of COVID impact but will be kept under monthly review. Consequence has been scored at 4 (major) because there is a risk of significant variations in quality of and access to care for patients if the priorities are not delivered. A number of areas are challenging and not delivering due to additional demand in the system and time required for demand to be addressed to reduce the back log plus P3 restoration targets
Current | 5 | 4 | 20
Appetite | 3 | 4 | 12
Approach | Treat
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Programme Governance arrangements
Steering Group: On track. CCG Contracting process: Reporting requirements relating to cancer coming via contracting. 6 weekly reporting to BCSG about minimising harm and restoration programme delivery progress plus areas that require escalation. | [5 empty] | HQS implementation group established, to develop and monitor quality priorities including CDG aim to reduce clinical variation and define quality measures for the CA programme. CCG will continue supporting at ICS/CA level via membership of group and CE CCG and Cancer Lead representation at CA board and CA Quality board . Steering group meeting 6 weekly and produces 6 weekly programme assurance and risk register that is approved by steering group and shared with CA. This group monitors programme delivery and updates shared with CCG SRO An 6 monthly assurance report submitted for governing body. contracting process ensures controls in place for BHNFT and STHT performance and contractual totals. This is reported to CCG via Finance & Performance committee and CQB /Quality and patient safety via Chief Nurse . 6 weekly reporting to SMT about minimising harm and P3 restoration programme delivery progress plus areas that require escalation. 6 weekly reporting to SMT about minimising harm and P3 restoration programme delivery progress plus areas that require escalation delete | [5 empty] | Ongoing
62 Day Waits and 28 FDS
Current CCG performance for 62 RTT validated performance is 76 % at November 2021. (target 85%). Challenged pathways remain as Lower GI and Urology . Cancer patients remain first priority by BHNFT services . 28 FDS is for 65% December 2021 ( 75% target by October 2021 ) , main challenged tumour pathways are lower GI and Urology . To meet the target audit undertaken to identify how can improve referral form and tests completion so that BHNFT can triage and meet FDS target, employed patient tracking co-ordinators BHNFT to unblock any hold ups. PCN trialling using care-cordinators to support referral process . | [5 empty] | Performance is reported to CCG via Finance & Performance committee and via CA board reporting arrangements. CCG meets BHNFT cancer lead weekly to monitor performance and gain assurance about improvement actions to address minimising COVID impact and P3 restoration. Steering group meeting 6 weekly and produces monthly programme assurance and risk register that is approved by steering group and shared with CA. This group monitors programme delivery and updates shared with CCG SRO monthly . Restoration plan agreed with BHNFT by CCG. DON gaining assurance about maintaining quality from BHNFT and STHT during restoration period. | [5 empty] | Ongoing
Prevention
Cervical started June 2020 Bowel restarted early September and Breast screening 5 days mid- September .CCG raised at BHNFT CQB that breast screening staff capacity is a risk and impacting on restoration. Extended Cervical screening running again via I-HEART .PHE provided additional recovery funding to BHNFT for Breast screening backlogs. | [5 empty] | Assurance is via 6 weekly cancer programme assurance process that ensures programme is on track and lack of progress addressed. The BCS work is reported to CCG via contractual process, via leads attendance at CCG Steering Group and bi-monthly assurance meetings with BCS by CCG cancer programme lead. Out of hours cervical screening pilot monitored via existing I-Heart contract assurance . Breast screening additional machine in place and new staff start in April 2022 to stabilise the servce delivery and recovery.
Early Diagnosis
Timed pathways: All timed pathway been affected - Lung, Lower & upper GI & urology (red rating ): not meeting 28 day STT FDS. Endoscopy started extra slots and having an impact but still have 62 day breaches for RTT. BHNFT signed up to ICS endoscopy remote radiology procurement to increase capacity. Community diagnostic pathways/hub planning started and mapped overlaps with ICS elective care areas Scoping being undertaken with BHNFT and PCN . Will identify pathway efficiencies and how can reduce demand on current pathway. PCN agreed Early diagnosis DES project action plan with CCG – to reduce the variation in screening and early diagnosis rates across PCN practices and within the different Neighbourhood areas. Vague symptoms pathway Re-launched with the start of Cthe Signs and referrals are increasing. . | [5 empty] | Assurance is via 6 weekly cancer programme assurance process that ensures programme is on track and lack of progress addressed. CCG attends CA monthly ED group and reports back to CCG actions and ensures actions agreed are adopted via CCG governance routes including reporting and gaining approval at MT for vague symptoms pathway and lower GI pathway implementations. CCG attends CA monthly ED group and reports back to CCG actions and ensures actions agreed are adopted via CCG governance routes including reporting and gaining approval at MT for vague symptoms pathway and lower GI pathway implementations. | [5 empty] | Ongoing
Better treatment and care
Waiting times: Start again rolling out timed pathway to reduce pressure on system. Tele dermatology : CCG Gov body agreed VEAT & contract to 31/12/2022- All 104 breaches had a RCA undertaken and safety netting in place by BHNFT for all patients on 2WW and routine pathway. Raised at CQB BHNFT that concern about breast screening and urology pathway quality due to staff turn over and increase in serious incidentreporting . Produced harm reduction policy with CA that is more holistic definition that includes psychological harm of being on a prolonged pathway - in place .Non-medical oncology staffing levels at critical level - risk mitigation actions in place to reduce the impact on patient choice and additional temporary chemotherapy unit opened at Burleigh medical centre to increase patients access in a Barnsley location. | [5 empty] | Assurance is via monthly cancer programme assurance process that ensures programme is on track and lack of progress addressed. CCG attends CA monthly operational group and reports back to CCG actions and ensures actions agreed are adopted via CCG governance routes including reporting and gaining approval at MT and clinical forum . Quality Surveillance self-assessment reported to CCG quality and safety committee annually and exceptions raised via this route . Chief Nurse gaining assurance about maintaining quality from BHNFT and STHT during recovery period via Q&PSC remit . Risk to Barnsley population due to temporary change in non-oncology face to face appointments at BHNFT not being available. Placed on CCG risk register December 2021 – oversight for this risk is via the CCG QPSG remit- mitigation is that STHT collecting appointment uptake figures each month to evaluate the impact and to readdress this impact . | [5 empty] | Ongoing
LWABC
e-HNA/Care planning: Live pilot continues. CSW roles appointed. All templates completed in the 3 tumour sites. Supported self management: The Well has moved and reopened for face to face . Anxiety managements courses are well-attended. Risk stratified pathways: Clear pathways in place and being agreed regionally and locally –some prolonged delays on local completion - working BHNFT to address. New men's peer group for prostate cancer completed and being taken foward as outcomes were positive . | [5 empty] | Barnsley LWABC steering group governance framework in place and LWABC Leads membership of CA LWABC programme ensures programme reported to CCG | [5 empty] | Ongoing
End of Life
EoL strategy group meets to progress action plan - new objectives/actions agreed. Plan in place that is focusing on increasing early care planning for patients and staff , proposal for a community based Consultant in palliative care been produced. Palliative care GP for ICS and Barnsley engaging with practices to identify how EOL working can be improved and working on supporting PCN. | [5 empty] | Reporting is via CCG being member of EOL strategy group and having responsibility to ensure strategy action plan on track. CCG reporting of Care homes ANP work plan gained by attending 1/4 implementation group and via CCG care homes programme governance. EOL group focusing on reducing unavoidable admissions and early identification- action plan in place. EOL within D2A monitored by OH governance and via Chief Nurse | [5 empty] | Ongoing
Communication and engagement
Barnsley Resilience group started working on deliverables to reduce people’s concerns and to target those that have unequal access to diagnostics and/or treatment or making choice to not engage - targeted communication undertaken by BMBC and ALMO housing provider staff and clients to dispel myths/concerns about using services and advertising alternative support services in place to help them have access e.g. NHS volunteer transport options. | [5 empty] | Assurance is via 6 weekly cancer programme assurance process that ensures programme is on track and lack of progress addressed; The CCG via CA established communication and engagement and Barnsley Communication and engagement group ensures actions and reporting are to CCG and via 6 weekly reporting for the cancer programme assurance reporting. Behavioural insight trials and wider work is targeting groups that have not returned to services compared to pre-covid. Communication and engagement linked into BMBC local areas council forums and structures to widen coverage .
Gaps in assurance | [6 empty] | Positive assurances received
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Tolerance | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20

## 3.2
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 3.2: MAXIMISING ELECTIVE ACTIVITY |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
There are four key areas of work: 1. Clinical Prioritisation - Continue to prioritise the clinically most urgent patients and address the longest waiters whilst ensuring health inequalities are tackled. • Greatest Harm - Incorporate clinically led, patient focused reviews and validation of the waiting list on an ongoing basis, to ensure effective prioritisation and manage clinical risk • Build on the established clinical priorisation tool (FSSA recovery prioritisation matrix) to support the prioritisation of all referrals & draw on both primary and secondary care knowledge • Long waiters - Focus on reducing the number of 52 week waiters by end of March 2022, ensuring plan includes analysis of waiting times by ethnicity and deprivation 2. Communication - maintain effective communication with patients including proactively reaching out to those who are clinically vulnerable. • Develop a system wide communications plan to inform public of approach and maintain effective proactive communication with patients. 3. Embedding Outpatient Transformation - support prioritisation in elective activity by minimising outpatient attendances of low clinical value and redeploying that capacity where it is needed. • Advice and Guidance - (Maintain) Increased mobilisation of advice and guidance to provide specialist advice (this supports low conversion rates to outpatient appointments) • Patient initiated follow-up (PIFU) - Expansion of programme so that PIFU is available in at least three major outpatient specialties by the end of Q2. • Remote Appointments - Where outpatient attendances are clinically necessary, at least 25% should be delivered remotely by telephone or video consultation (equivalent to c.40% of outpatient appointments that don’t involve a procedure). 4. Elective Activity / Elective Recovery Fund • Monitoring elective recovery against the 95% target: From July 2021 deliver 95% of all electivity delivered in 2019/20 from July 2021 (and over 100% for those part of the accelerator programme via use of independent sector and insourcing) |  |  |  |  | Highest quality governance |  |  | There is a risk that the CCG will not be able to maximise elective activity if the following issues are not mitigated: 1. Clear and effective communication to the public about delays to treatment and prioritsation. 2. Where necessary improve uptake of residents to travel outside of barnsley for treatment. 3. If patients do not present for treatment. 4. If patients have a preference for face to face appointments. 5. workforce capacity to deliver over 85% of activity (taking into account IPC, social distancing, staff leave, burnout as well as access to diagnostics) 6. provider headspace to undertaken pathway transformation and adopt new ways of working e.g. PIFU
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
C1 - Maximise elective activity
Committee Providing Assurance |  |  | TBC | Executive Lead |  |  | JW | Clinical Lead |  |  |  | MG,MS,JM
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 3 | [5 empty] | Rationale: Likelihood has been scored at 3 (possible) but will be kept under review. Consequence has been scored at 4 (major) because there is a risk of significant variations in quality of and access to care for patients if the priorities are not delivered.
Current | 3 | 4 | 4
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Barnsley system Planned Care and Outpatients Group has been established and meets monthly, with CCG attending, to discuss system wide approach planned care, outpatient transformation and elective care recovery. This supports a system overview of the issues as well as to make improvements to system pathways and relationships. | [5 empty] | Chief Operating Officer, CCG Medical Director and 2 x Governing Body members are represented on the board. Work is ongoing to align the elective care system wide plan to the planning Guidance and other NHSE Guidance on the transformation of outpatients / specialty redesign. The group has recently established the scope of 'elective care' and set key deliverables for 2021/22. | [5 empty] | Ongoing
The CCG and Trust are leading on the developing a clear, prioritised delivery plan and Communication and Engagement Plan | [5 empty] | Planned Care Board is established to provide oversight of the programme. The Board has representation from all partners. Clear priorities have been agreed as part of development of the Barnsley Place Plan. Comms and Engagement Plan is being delivered as part of wider system work around pressures in the H&SC system | [5 empty] | In Progress
Operational planning process for the 2021/22 has been completed in line with the NHS Planning Guidance. All activity plans are in line with national expectations for increased activity levels back toward those in 2019/20, reflecting local restrictions and transformation work to redesign services. | [5 empty] | Chief Operating Officer, CCG Chair and 2 x Governing Body members are represented on the Planned Care board. Work is ongoing to ensure alignment of the elective care system wide plan to the planning Guidance and other NHSE Guidance on the transformation of outpatients / specialty | [5 empty] | Ongoing
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
Planned Care – backlog and demand surge There is a risk of delay to treatment of patients either through restricted access to services (due to social distancing, IP&C, need to travel) or hidden harm through people failing to present with issues due to fears around covid. This is likely to result in an increased number of poorly managed chronic conditions or undiagnosed diseases. | [6 empty] | • All listed patients are clinically triaged, priority patients have been treated throughout the year, a green pathway and protected bed capacity have been agreed. • Patients with LTC have also been reviewed and prioritised in primary care. • Primary, community, mental health , outpatients and diagnostics services remain open. • Long waiters for Barnsley place are being reviewed and actions being taken to further support improved care delivery. • A system wide comms plan has been drafted to help maintain effective communication with patients including proactively reaching out to those who are clinically vulnerable.
Elective Pathways There is a risk of delay to treatment of patients on elective pathways. This is caused by restrictions in terms of ipc and royal guidance re green sites e.g. orthopaedics. The impact will be to quality of life for individuals awaiting their operation and increased pressure on services to deliver. A further issue is the reticence of local residents to travel outside of Barnsley for treatment. | [6 empty] | • All patients have been clinically triaged with emergency and urgent cases being seen. External assurance has been obtained through national clinical validation exercise. • System planned care group supports a system overview of the issues. • Green pathway is now in place and dedicated beds for elective orthopaedics • Use of Independent sector and mutual aid. • Plans have been updated in response to the 21/22 planning guidance and participation in the elective accelerator programme (enhancing plans to deliver capacity beyond 85%, to excess of 100% from July 2021). The work will focus on streamlining and developing pathways in key surgical specialties (orthopaedics, ophthalmology, paediatrics) and work with IS Sector. Local work is focused on PIFU and comms.
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 4.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 4: MENTAL HEALTH |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
A Barnsley Mental Health Partnership Board has been established, reporting directly to the Barnsley Health and Wellbeing Board and supported by a system-wide Mental Health Delivery Group. We continue to increase the number of children and young people receiving evidence-based treatment to improve their emotional health and wellbeing through the redesign of the CAMHS service and inreasing the number of MHST's and commissioning third sector organisations - the access target to be achieved in 2021/22 is 57% - CAMHS service beginning to implemement the new co-produced service specification focusing on establishing a Single point of Contact. A Children and Young People's Emotional Health and Wellbeing Hub is being developed on the first floor of the YMCA Building in the centre of Barnsley. A Children and Young Peoples Transformation Lead now in situ and leading on implementing recommendations of Overview and Scrutiny Committees which are also supported by the CCG IAPT services to be expanded to the level of investment available and working towards delivering the recoemmendations of the NHS Long Term Plan. Access targets will be challenging and the recommended targets unlikeley to be achieved. IAPT recovery target consistently above the national recommended target of 50% and support improving the recovery rate to an ambitious target of 60% Community Mental Health Transformationb bid successful and work progressing to develop a local Adult Eating Disorder pathway to link in with the regional service development led by RDASH as part of the SYB ICS; transformation funding also being utilised to develop improved services for people with Personality Disorders and to enhance Community Mental Health Rehab services linking with the newly developed Primary Care Mental Health posts as part of the ARRS (Additional Roles Reimbursement Scheme). Crisis Alternative bid has been successful and work is progressing to provide a 'safe space' for adults as part of the mental health crisis care support within the borough (it is anticipated that the childrens and young peoples Hub will provide a 'safe space' for children and young people as it evolves). Self-harm contines to be a key focus, particularly in the 10 - 24 years old age ranges where admissions to hospital in Barnsley are almost double the national average - Public Health are leading on work to reduce these admissions and provide more appropriate, early intervention. All-age liaison mental health (CORE 24) service now fully operational. Exemplar work progressing in Barnsley in respect of suicide prevention with targeted work continueing to be undertaken re men and older people. Specialist Perinatal Mental Health Services esablished and funding agreed to achieve the necessary expansion to achieve the LTP access requirements for 2021/22 Work is progressing to develop a single neurodevelopmental pathway for children and young people with the potential of achieving an all-age pathway within the next two years The Mental Health Investment Standard (MHIS) will be ahcieved. Improve access to healthcare and deliver annual physical health checks for the population - the target to be achieved for 2019/20 of 60%was not achieved for patients on the GP SMI Register and improvements need to be made. 66.7% of people with dementia aged >65 should receive a formal diagnosis. |  |  |  |  | Highest quality governance |  |  | There is a risk that if the CCG and its partners are unable to manage and mitigate the potential barriers to improving mental health services - lack of workforce capacity, limited financial resources, and legacy 'backlogs' - the CCG's ambitions for these services will not be achieved and that delivery of the recommendations within the NHS Long Term Plan (as explicitly outlined within the Mental Health Implementation plan 2019/20 - 2023/24) within the expected timeframes will not be possible
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
C3 - Expand and improve mental health services and services for people with a learning disability and/or autism
Committee providing assurance |  |  | FPC & QPSC | Executive Lead |  |  | PO | Clinical Lead |  |  |  | Dr M Smith
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 4 | 3 | 12
Current | 4 | 3 | 12
Appetite | 4 | 3 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
The Future in Mind funding allocations are now part of the CCG's baseline allocations and will continue to be utilised towards delivering the ambitions of the NHS Long Term plan | [5 empty] | Quarterly Assurance reports / feedback to NHS England; monitored by C&YPT(Children and Young Peoples Trust) ECG (see note 1). ECG minutes to F&P Committee. Chilypep Quarterly monitoring reports | [5 empty] | Ongoing
Perinatal Mental Health - continue to implement the specialist perinatal health team and to fund the specialist mental health midwife post at BHNFT. | [5 empty] | ICS Reporting Framework. Regular updates to Governing Body. Mental Health service transformation overseen by the Mental Health Delivery Group | [5 empty] | Ongoing
Service provider developing robust workforce plans in conjunction with Health Education England National Workforce Strategy - a local SWYPFT workforce strategy has been developed - SYB ICS Programe Board are leading on a regional wporkforce strategy to cover the next 5 years | [5 empty] | Monitored at ICS level SYB ICS MHLD Steering Group. | [5 empty] | Ongoing
Commissioning capacity for the adult autism service has been increased for 2021/22 and non-recurretn funding has been provided to eliminate the current backlog - by March 2022 it is anticipated that the current 3 year wait for an adult autism assessment will be reduced and sustained at 3 months. The newly commissioned service for the over 11 autism pathway has reduced the waiting time on this pathway from 2.5 years to a maximum of 9 months. All Barnsely's children and young peoples autism assessmentrand diagnositc pathwyas are fully NICE compliant | [5 empty] | Performance data from SWYPFT (Adult service) and BHNFT (CYP service). Minutes of the ASD Steering Group | [5 empty] | Ongoing
Continue to promote the local social prescribing service and the Children and young Peoples's Social Prescribing Service provided by the Barnsley Healthcare Federation | [5 empty] | CAMHS Performance data received monthly and presented at ECG on a quarterly basis. Compass data in development. Chilypep provide a quarterly performance report that his shared with GB. Autism activity data in development and overseen by the Autism Steering Group | [5 empty] | Ongoing
IAPT access targets are a key challenge in Barnsley - ther service is continuously promoted on social media and at GP surgeries and other community centres and self-referrals enabled via the Barnsley IAPT website. Limited university training places remain a constricting factor but HEE undertake to increase the places availalbe in future years. | [5 empty] | Oversight by F&PC, reporting into Governing Body. New IAPT service is fully implemented and all national IAPT targets are achieved with the exception of the access targets - this reflects the regional picuture. Work is underway via the SYB ICS MHLD. Minutes of the SYB ICS MHLD Steering Group. | [5 empty] | Ongoing
Barnsley Mental Health Partnership and a supporting Mental Health Delivery Group (MHDG) has been established which is providing robust oversight of the issues and challenges facing the local population. The work of the Crisis Care Concordat and Suicide Prevention Group is now merged in to the MHDG. Improved system-wide intelligence and mental health data is supporting improved decision making and providing additional assurance. | [5 empty] | Mental Health Partnership Board report to Barns;ey Health and Wellbeing Board | [5 empty] | Ongoing
Barnsley CCG's bid for a MHST (as part of the Trailblazer programme) was successful and following a competitive procurement process Compass were awarded the contract. Recent bids as part of Waves 5 - 10 were submitted and Barnsley have been successful as part of Wave 8 (i.e. an additional MHST team will be funded by NHSE/I in 2022/23) with a possibility of a further team in Wave 10 (2023/24) | [5 empty] | A small working group of key stakholders has been established to drive the transformation of the CAMHS service towards delivering the new service specification based on the iThrive model- this group reports to both the ECG and CCG Governing Body. CCG clinical leads support this group. | [5 empty] | Ongoing
Barnsley CCG's bid to develop a Crisis Alternative and to access Community Mental Health Transformation Bids have been successful. Implementation of these bids is being overseen by the Mental Health Delivery Group and monitored / supported closely by SYB ICS MHLD Programme Board. | [5 empty] | Performance and activity data submitted via contracts process. Quarterly Mental Health updates to CCG Governing Body | [5 empty] | Ongoing
Note (1) - the Childrens & Young People's Trust ECG minutes go to F&PC for information. It reports via TEG to H&WB which is attended by the CCG Chair and CO and minutes go to GB. Specific issues may be raised with GB via regular 6 monthly / ad hoc Children's Services updates.
Gaps in assurance | [6 empty] | Positive assurances received
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Consequence | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 5.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 5: INTEGRATED CARE SYSTEM (ICS) |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
System Level: There is a shared view that in order to transform services to the degree required to achieve excellent and sustainable services in the future, we need a single shared vision and plan in each Place and across South Yorkshire and Bassetlaw. Partners from across health and social care in each Place have come together to develop a single shared vision and plan as part of an Integrated Care System. |  |  |  |  | Highest quality governance |  | ü | The effectiveness of commissioning at place level across the full range of CCG priorities could be detrimentally affected if uncertainty re the future of commissioning across the system leads to disengagement or loss of capacity or direction locally. Effective governance of the ICS, changing role of the ICS eg allocation of funding to CCGs and providers . Managing change to system working during a pandemic could cause capacity issues, uncertainty for all stakeholders and could limit long term decision making.
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
CCG contributions to system wide working & enabling work streams: Leadership and programme support System-wide governance arrangements (including a system partnership board with NHS, Local Government and other partners) to enable a collective model of responsibility and decision-making between system partners. System capabilities including population health management, service redesign, workforce transformation, and digitisation required to fulfil the two core roles of an ICS. Agreed ways of working across the system in respect of financial governance and collaboration for 22/23. Capital and estates plans at a system level, as the system becomes the main basis for capital planning, including technology. Plans for how the system will iperate in 2022/23 will need to finalised for April 22. White paper on the formation of statutory ICS published Dec 20 with an ambition for statutory ICS to form in July 2022, legislation going through parliament and designate appointments are being made |  |  |  |  | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
F1 &F4 - Effective collaboration and partnership working across systems & Develop ICSs as organisations to meet the expectations set out in Integrating Care
Committee Providing Assurance |  |  | ICS CPB JCC of CCGs | Executive Lead |  |  | CE |  |  |  |  | NB
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 3 | 9 | [5 empty] | Rationale: Likelihood has been scored at 3 (possible) because individual organisation will be required to deliver on their statutory duties and may prioritise these over partnership commitments. Consequence has been scored at 3 (moderate) because whilst we would not be able to harness the full benefits of integrated health and care the commissioning and provision of health and care services for Barnsley people would continue.
Current | 3 | 3 | 9
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Governance review of the ICS currently underway to inforn how the system operates in 2021/22 | [5 empty] | Minutes of HOB and JCCCG | [5 empty] | Ongoing
Collaborative Partnership Board (CPB) provides strategic direction and oversight of the ICS, while the Joint Commissioning Committee of CCGs facilitates collective commissioning decisions over defined areas. | [5 empty] | Minutes of both CPB and JCCC of CCGs are taken through the Governing Body | [5 empty] | Ongoing
ICS Memorandum of Understanding signed by all parties in place outlining sign up to direction of travel in system and in place, recognising journey to local Integrated care partnerships | [5 empty] | ICS MOU signed off by Governing Body and all Parties to the ACS for 17/18. MOU for 2018/19 between NHSE/I and ICS agreed and signed off by 1 October 2018. ICS go Live October 2018.Integration agreements between place and system developed(from October 2018 ). | [5 empty] | Complete (Oct-18)
Clear governance arrangements in place to enable to ICS to make both collective commissioning and provider decisions through the Joint Committee of Clinical Commissioning Groups (JCCC) and Providers Committee in Common (CiC) | [5 empty] | Minutes of both CPB and JCCC of CCGs are taken through the Governing Body. ICS governance arrangements for Level 3 ICS from April 19 in place | [5 empty] | Complete
The ICS has a clear management structure with sufficient capacity and resources to take forward its transformation programmes on behalf of the system. | [5 empty] | Agreement of 2018/19 ICS nationally allocated transformation funding and partner contributions and sign off of 2018/19 ICS budget. Revised ICS Executive Management Team in place. | [5 empty] | Complete
Development of Barnsley Integrated Care Partnership (ICP) ensures strong Barnsley voice into the SYB ICS to influence the creation of the Statutory ICS. | [5 empty] | Barnsley Place agreement finalised. Barnsley Health and Social care plan produced. | [5 empty] | Complete
Collective approach to decision making in relation to the Hospital Services Review in place within the Barnsley partnership and across the ICS. | [5 empty] | Hospital Services Review received both by ICS Collaborative Partnership Board and by Barnsley CCG Governing Body. Governing Body agreed to the publication of the Strategic Outline Case October 2018. | [5 empty] | Complete
Gaps in assurance | [6 empty] | Positive assurances received
• Ref 18/02 (rated score 16 ‘extreme’) - If the CCG and BMBC do not develop a collaborative commissioning approach underpinned by shared values there is a risk that BMBC commissioned services will not meet the requirements and aspirations of the CCG for the people of Barnsley leading to increased health inequalities and poorer health outcomes. | [6 empty] | SYB response to the NHS Long Term Plan collectively developed across partnership. Barnsley Partnership agreement completed. Barnsley Health and Social Care plan agreed.
governing body receives regular updates, HEG minutes and every other month meets as the focussing on the transition to ICB
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Risk rating | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 5.2
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 5.2: INTEGRATED CARE AT PLACE LEVEL |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
Development of partnership arrangements in Barnsley that deliver integrated services for patients and service users and create a weight-bearing structure in Barnsley to support maximum delegation with the integrated system from April 20222. This will include - -Development of the primary care network and neighbourhood networks - Embedding population health management to improve outcomes across the borough and targeted local action on health inequalities - Left-shift of investment and provision from secondary care to primary, community and out-of-hospital care - Strengthen joint commissioning between the CCG and Barnsley Council - Workforce and organisational development to system leadership and working - Growing the workforce for the future - Optimum use of the health and care estate across the borough and investment to facilitate shift of activity from hospital into community - Development of integated governance and shared leadership - Supporting and promoting the role of the community, voluntary and social enterprise sector in Barnsley in health and care |  |  |  |  | Highest quality governance |  | ü | There is a risk that if the following threats are not effectively managed and mitigated the key deliverables will not be achieved: - Financial pressures and maturity of the local partnership to manage risk - Uncertainties around the development of the integrated care system and role of place with the system and lack of clarity about the role and expectations of provider partnerships - Challenging timescales for organisational change with the reading of the draft integrating care bill delayed - The Government may fail to bring forward a legislative programme for adult social care and financial settlement or that the expected white paper does not fully support the developing partnership working in Barnsley - Clarity of the role of Barnsley Health and Wellbeing Board and local democratic accountability in the new system - Role of GPs and clinical commissioning in the new system - Staff retention through COVID recovery and system change - Ongoing COVID pandemic and associated pressures across services, particularly sustainability of the urgent and emergence care model in Barnsley and capacity of providers to constructively engage in development of the place partnership - Impact of COVID on the community, voluntary and social enterprise sector - Failure to demonstrate the impact and benefits of new ways of working in order to generate support and increase engagement - Lack of capacity to support expansion of student placements - Ability to recruit into new roles including additional roles in primary care - Sufficient focus and investment in transformation
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
A - Supporting the wellbeing of staff and take action on recruitment and retention (esp A4 grow for the future - system workforce planning) F1 & F2 - Effective collaboration and partnership working across systems & Develop local priorities that reflect local circumstances and health inequalities
Committee Providing Assurance |  |  | Governing Body | Executive Lead |  |  | JB | Clinical Lead |  |  |  | NB
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 12 | [5 empty] | Rationale: - Major (4) impact due to possibility of adverse local media coverage, potential slippage leading to a key objective not being met and potential for external challenge - Likely (3) as it is possible that the impacts could recur occasionally
Current | 3 | 4 | 12
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Joint priorities and work programmes | [5 empty] | Barnsley Health and Care Plan 2021/22 developed with partners and endorsed by the integrated care partnership group. | [5 empty] | Ongoing
Oversight from the CCG Governing Body | [5 empty] | Regular updates on integrated care received by Governing Body. Discussions at Governing Body Development Sessions. Representation from Governing Body by the Chair and Accountable Officer at Integrated Care Partnership Group meetings. Clinical leadership from Governing Body across partnership priority workstreams. | [5 empty] | Ongoing
System engagement including primary care | [5 empty] | Series of BEST events focussed on emerging guidance for primary care networks and the right model for Barnsley. Membership Council agreed to strategic direction at the meeting held on 3 July 2018 | [5 empty] | Complete
Local partnership governance arrangements | [5 empty] | Compact and place agreement. Memorandum of Understanding between SWYPFT and the PCN for joint leadership. Senior responsible officers for all priorities set out in the Health and Care Plan | [5 empty] | Complete
Alignment of resources | [5 empty] | CCG commissioning and transformation staff aligned to partnership delivery groups. Additional interim support for the place design team | [5 empty] | Complete
Independent legal advice | [5 empty] | Appointed legal advisors that are also supporting the ICS and work nationally on integrated care. | [5 empty] | Complete
Voice of place in the development of the integrated care system | [5 empty] | Representatives of place on each of the ICS design workstreams and provider collaboratives feeding back into the place design team and integrated care partnership | [5 empty] | Complete
Communications and engagement | [5 empty] | Communications leads from across the partners have co-produced a communications and engagement place that has been signed off by ICPG. | [5 empty] | Complete
Strong links between place and ICS workforce hub | [5 empty] | Appointment of place workforce lead to work with the ICS workforce hub. Representation at the Local Workforce Action Board. Working with the ICS workforce hub on system priorities and alignment of local priorities including Barnsley Health and Social Care Academy, Project Echo and school engagement | [5 empty] | Ongoing
Student placement expansion project | [5 empty] | Appointed to a coordinator role to support student expansion hosted by Barnsley Hospital. Agreement to explore a place-based allocation model beginning with pre-registration nursing students. Completed CLiP project with ongoing evaluation | [5 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
Establishment of a PMO function to support delivery of the health and care plan | [6 empty] | Proposals being developed and will be presented to ICDG in July 2021. Proposals will ensure alignment of resources from across the partnership to support delivery
Pending guidance from the Department of Health and Social Care and NHS England Improvement regard constitution of integrated care systems and transitional arrangements | [6 empty] | Place design team established and jointly Chaired by the CCG Accountable Officer and BMBC Chief Executive. Undertaken a self-assessment using the ICS Place Development matrix to identify priority areas and actions. Agreed preferred options for weight-bearing structure at Place. Ongoing discussions across SYB ICS leaders and Place leaders around preferred operating model
Development of collaborative commissioning | [6 empty] | A series of workshop with CCG and BMBC commissioners to agree a joint approach around the life course. Developing a commissioning plan to support delivery of the Barnsley Health and Care Plan with CCG Governing Body.
Workforce strategy is overdue for review and update | [6 empty] | Place workforce lead recently appointed. Planned refresh of the strategy over the summer 2021
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 5.3
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 5.3: IMPLEMENTING POPULATION HEALTH MANAGEMENT AND PERSONALISED CARE |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
The CCG, local and system partners are committed to embedding a population health management approach to target recovery strategies, aiming for equitable access, excellent experience and optimal outcomes for all groups. This includes - - Use of person-centred segmentation and risk stratification to identify at-risk groups, those with the greatest health inequalities or the most complex needs, and those awaiting multiple appointments - Provide proactive, multidisciplinary, cross sector support to these patients, in line with the NHS Comprehensive Model for Personalised Care - Developing robust plans for the prevention of ill-health such as expansion of smoking cessation services, improving uptake of the NHS diabetes prevention programme and CVD prevention and high impact actions to support stroke, cardiac and respiratory care - Accelerating the delivery of existing requirements, including personal health budgets, social prescribing referrals and personalised care and support plans |  |  |  |  | Highest quality governance |  |  | There is a risk that the CCG will not be able to successfully implement Population Health Management and Personalised Care if the following issues are not mitigated: - Lack of capacity in primary and community care to support delivery because of ongoing operational pressures - Failure to successfully recruit, train, develop and retain additional roles in primary care including social prescribing link workers, care coordinators and health and wellbeing coaches - Ability to access linked person-level data to identify priority cohorts, target interventions and demonstrate outcomes and impact - Lack of sufficient technical analytical capability and tools to support delivery - Failure to properly engage and involve people in decisions about their care and service development
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
D2 - Implementing Population Health Management and Personalised Care
Committee Providing Assurance |  |  | TBC | Executive Lead |  |  | JB | Clinical Lead |  |  |  | Dr M Guntamukkala
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 3 | 9 | [5 empty] | Rationale: - Major (3) impact due to potential slippage leading to a key objective not being met and potential for external challenge - Likely (3) as it is possible that the impacts could recur occasionally
Current | 3 | 3 | 9
Appetite | 3 | 3 | 9
Approach | Tolerate / Treat
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Executive leadership and sponsorship | [5 empty] | Designated executive leads for tackling health inequalities across all NHS partner organisations. Workshop for health inequalities leads and integrated care delivery group representatives with outputs and framework endorsed by ICPG. Health inequalities cross-cutting theme in Barnsley Health and Care Plan 2021/22 that has been endorsed by partners | [5 empty] | Ongoing
Improving health intelligence infrastructure across the partnership | [5 empty] | Health intelligence group established with positive engagement from across the partnership. Population segmentation analysis completed. Population health management analyst hosted by Barnsley Hospital funded through COVID monies. Increased information sharing through COVID and high-level agreement endorsed by all partners. Regular reporting of health surveillance. Integrated Care Outcomes Framework adopted by ICPG and Barnsley Health and Wellbeing Board | [5 empty] | Ongoing
Risk stratification tool to support proactive case finding | [5 empty] | Eclipse platform embedded within medicines management team. Sharing of secondary care data into Eclipse for pathway development | [5 empty] | Ongoing
Prevention programmes in place and/or in development | [5 empty] | Warm home healthy people team. Shaping Places Healthy Lives. My Best Life social prescribing service. Primary care network social prescribing link workers, care coordinators and health and wellbeing coaches. Diabetes prevention programme. Barnsley Hospital Health Lives Team established. Barnsley Hospital selected to pilot an Alcohol Care Team. Get fit first in place to support people to lose weight and stop smoking before surgery to reduce risk of complications and achieve better outcomes | [5 empty] | Ongoing
Personalised budgets | [5 empty] | Embedding with NHS Continuing Healthcare practice and adult social care | [5 empty] | Ongoing
Personalised care planning | [5 empty] | Patient activation measures embedded with the SWYPFT long term conditions management services. Year of care in primary | [5 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
Pending publication of PCN service specification for anticipatory care | [6 empty] | Working group established to develop proactive care model focussed on mild to moderate frailty building on the learning from supporting vulnerable people through COVID and population segmentation analysis. Ongoing work with NHS Prescribing Solutions to configure local pathways for Barnsley beginning with frailty. Development of the Barnsley Vulnerability Index
Pending publication of PCN service specification for personalised care | [6 empty] | Personalisation is identified as one of the cross-cutting themes of the Barnsley Health and Care Plan 2021/22. Providing joint training and development opportunities for health and care staff including strengths-based practice and shared decision making is one of the priorities of the Barnsley Health and Care Plan being taken forward through the workforce group
Strength and balance offer for people at risk of falls | [6 empty] | BMBC have identified funding and proposals are in development to strengthen the local prevention offer for healthy ageing
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Risk rating | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Tolerance | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9

## 6.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 6: FINANCIAL BALANCE & EFFICIENCY PLANS |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
• Free up hospital beds • Best value across all CCG expenditure • Reduce avoidable demand • Reduce unwarranted variation in clinical quality and efficiency • Financial accountability and discipline for all trusts and CCGs • Deliver financial balance in 2021/22 |  |  |  |  | Highest quality governance |  | ü | There is a risk that the continuation of the 2020/21 financial regime limits the CCGs ability to deliver efficiency due to the impact of the Covid-19 pandemic and block contract arrangements in place for all NHS providers. Development of plans is critical in order that the CCG can achieve its statutory duty to breakeven with a balanced budget position for 2022/23.
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
F5 - Implement ICS-level financial arrangements
Committee Providing Assurance |  |  | FPC | Executive Lead |  |  | RN | Clinical Lead |  |  |  | Various
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 4 | 4 | 12 | [5 empty] | Rationale: Likelihood currently judged to be likely and will be kept under review. Consequence judged to be 'major' in light of potential impact on statutory duties, performance ratings, and organisational reputation.
Current | 3 | 4 | 12
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Structured project management arrangements in place to support delivery | [5 empty] | Monthly reports to Finance & Performance Committee and Governing Body | [5 empty] | Ongoing
QIPP Delivery Group continues to be in place to maintain oversight of the QIPP programme a system wide efficiency group is also in place to ensure costs can be taken out of the system across partners | [5 empty] | Ongoing engagement with primary care, secondary care and internal management to support delivery of schemes, with a view to taking costs out of the system and ensure effective use of the Barnsley £. | [5 empty] | Ongoing
Clinical Forum provides clinical oversight of projects | [11 empty] | Ongoing
Continued development and review of the CCG's Medicines Optimisation QIPP 2021/22 to deliver prescribing efficiencies (high value scheme) | [5 empty] | Clinical Pharmacists and Medicines management team continue to engage with Primary care and a validation of all efficiencies reported as delivered is undertaken within the Medicines Management team. Medicines optimisation schemes have been commenced and the impact will be reported. There is a potential risk due to the covid vaccination programme that Prescribing QIPP may be restricted but this will be monitored with the Head of Medicines Management. | [5 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
The CCG will deliver its financial duties in 2021/22 and will report delivery of efficiences on a non recurrent basis and it expected to deliver a surplus year end position, however the wider objectives linked to this priority area are unlikely to be achieved due to the continnued impact of Covid-19. Discussions with partners remain positive and are ongoing in relation to the contract position for 2022/23 and beyond. Despite a lack of national guidance the CCG has begun developing its financial plan for 2022/23.
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
13/31 - There is a risk that if the CCG does not develop a robust QIPP plan supported by effective delivery and monitoring arrangements, the CCG will not achieve its statutory financial duties and NHS England business rules. | [6 empty] | The CCG is currently monitoring the efficiency plans in place around Prescribing and CHC. All other efficiency requirements will be met through reductions in expenditure given the impact of Covid-19 and the timescales to deliver plans. The programmes of work agreed at Governing Body do however need to continue to be progressed to ensure improved patient care and access as well as ensuring services remain financially sustainable through delivery of efficiency to close the gap that remains across Barnsley place from 2022/23 and beyond. Plans continue to be progressed, however the impact of Covid does remain a barrier to implementation and is likely to continue as we appproach 2022/23.
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 7.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 7: TRANSFORMING CARE FOR PEOPLE WITH LEARNING DISABILITIES AND / OR AUTISTIC SPECTRUM CONDITIONS |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
Transform the treatment, care and support available to people of all ages with a learning disability, autism or both so that they can lead longer, happier, healthier lives in homes not hospitals by: -Reduce inappropriate hospitalisation and lengths of stay to be as short as possible - Improve access to healthcare and deliver annual physical health checks (eg cervical screening) -Invest in community teams -Ensure all children with learning disabilities, autism or both receive Community Care, Education and Treatment Review (CETR) if appropriate - Ensure all adults with learning disabilities, autism or both receive Community Care and Treatment Review (CTR) as appropriate -Increase uptake on annual health checks and learn from learning disability mortality reviews Ofsted readiness in terms of the imminent local area Joint SEND Inspection Improve adult waiting times for autism and ADHD assessments - maintain the improvements within the Children and young peoples autism assessment and diagnostic pathways to ensure the pathwys remain NICE compliant |  |  |  |  | Highest quality governance |  |  | There is a risk that if the CCG and its partners are unable to provide focussed case management and wrap around services the following negative consequences may result: -People with a learning disability or autistic spectrum conditions will enter hospital inappropriately -There will be difficultly discharging current patients -Potential prohibitively high cost of meeting needs -Inability of current provider market to meet needs -Difficulty in ensuring that the quality of care is high - Insufficient funding to ensure the appropriate level of care within the community Insufficent funding to develop improved pre and post diagnostic support for people with autism / ADHD / LD
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
C3& E1 - Expand and improve mental health services and services for people with a learning disability and/or autism & Transforming community services and improve discharge
Committee providing assurance |  |  | FPC & QPSC | Executive Lead |  |  | PO / AR |  |  |  |  | Dr M Smith
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 4 | 3 | 12 | [5 empty] | Rationale: likelihood assessed as 4 'likely' because the local market is not sufficiently developed to enable all aspects of the transforming care plan to be delivered. Consequence judged to be moderate (3) because in terms of direct impact higher levels of care are viewed as 'safer' but longer term promoting independence and quality of life is compromised, hence this focus by NHSE.
Current | 4 | 3 | 12
Appetite | 4 | 3 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
A Complex Case Manager for Transforming Care patients has been in post from May 2019. The postholder will enusre CTR's and CETR's will be undertaken in a timely manner to ensure clients receive the most appropriate care in environments as close to Barnsley as possible. | [5 empty] | Commissioning updates provided to Governing Body with any Quality issues escalated to Quality & Patient Safety Committee. Twice yearly update reports to CCG Governing Body. Formal reporting / governance structure within the South Yorkshire and Bassetlaw Transforming Care Programme Board Monthly meetings held with all CCG's and the regional lead for the Transforming Care Programme. Weekly reports provided by the TCP Complex Case Manager to NHS E/I. | [5 empty] | Ongoing
Appropriate services are being developed within Barnsley, where apprpriate, to enable some of the most complex patients to return to Barnsley and be cared for within the local community. Detailed plans, with timescales, have been developed for each patient identified within the Transforming Care cohort, to return these patients to appropriate local community settings as quickly and as safely as possible to improve their life outcomes | [11 empty] | Ongoing
Formal reporting and Governance arrangements to transfer to the SYB ICS Transforming Care Programme Board whilst maintaining strong partnership arrangements with Calderdale, Wakefield and Kirklees (Transforming Care Partners CKWB). The West Yorkshire and Barnsley ATU provision has been re-designed and moves from 3 units to 2 units (based at Wakefield and Bradford) to deliver services as part of a Centre of Excellence. | [11 empty] | Ongoing
An all-age Autism strategy is being developed to support service transformation and improve the life outcomes of people with autism. | [11 empty] | Ongoing
An LD Strategic Health & Social Care Improvement Group has been established and is overseeing the action plan to improve the uptake of Annual Health Checks for people with LD and / or Autism. This group will also heavily influence the development of the autism strategy and connect the work progressing in terms of improving support for people with an LD and / or Autism. This group will also oversee the implementation of the keyworker role for children with autism and / or LD - currently there are keyworker pilots in operation in a number of South Yorkshire localities from which the learning will be shared - NHS E/I expect the children's keyworker role to be implemented by all areas no later than 2022/23. | [11 empty] | Ongoing
The SEND lead for the CCG has been identifed as the Head of Commissioning (Mental Health, Children's, Maternity). A Designated Clinical Officer has been appointed and will be line managed by the Specialist Clinical Portfolio manager who together will take responsiblity for the SEND agenda from a CCG perspective. Barnsley local area are still awaiting the CQC/OfSted Joint SEND Inpspection. The outcomes of the inspection will be shared with Governing Body members | [11 empty] | Ongoing
NHS E/I have amended the LeDeR review process. Local and regional processes will be enhanced / developed to ensure all learning from these reviews are embedded within practice within the Borough | [11 empty] | Ongoing
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
Plans are to be established to improve the uptake of Annual physical Health chekcs for people with LD
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Consequence | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 8.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 8: MATERNITY |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
Continue to work towards delivering the recommendations of 'Better Births' and the ambitions of the NHS Long Term Plan. implement the Saving Babies' Lives care bundle version 2 to further reduce still birth, neonatal deaths, maternal deaths and brain injuries. Implement the SYB LMS (Local maternity service) - - Improve maternity safety, choice and personalisation - Liaise closely with the local MVP (Maternity Voice Partnership) to ensure local women are able to influence and shape the delivery of future services Deliver all recommendations contained within the Ockenden report within the required timescales Achieve the recommended targets in respect of the continuity of carer model |  |  |  |  | Highest quality governance |  |  | There is a risk that the key deliverables will not be achieved if the following risks to delivery are not appropriately managed and mitigated: 1/ Lack of sufficient investment in additional staff resources to enable 'continuity of carer' 2/ LMS to oversee responses to Ockenden report and influence developments of all localities implementing the recommendations of 'Better Births' 3) LMS to invest transformation funding fairly within the locality to ensure local service developments can be implemented as agreed 4/ Lack of staff rotation between hospital and community based services may reduce the likihood of fully delivering continuity of carer
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
C4 - Deliver improvements in maternity care, including responding to the recommendations of the Ockenden review
Committees providing assurance |  |  | FPC & QPSC | Executive Lead |  |  | PO | Clinical Lead |  |  |  | Dr M Smith
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 4 | 3 | 12 | [5 empty] | Rationale: Likely primarily due to the staffing issue inherent in delivering continuity of carer and there are no additional funding streams available. Consequence is moderate because this is primarily a local issue which will potentially result in the late delivery of the key objective within the better birth recommendations of delivering the 'continuity of carer.'
Current | 4 | 3 | 12
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Continuity of carer teams are established in Barnsley and Barnsley is on track to achieve the recommended CoC target of 57% by March 2022. | [5 empty] | NHSE LMS assurance process | [5 empty] | Ongoing
CQB for each provider reports to Q&PSC | [5 empty] | Yorkshire and Humber maternity dashboard (enables benchmark) | [5 empty] | Ongoing
LMS oversight - Governing Body receive twice yearly / ad-hoc assurance reports | [5 empty] | Reporting into QPSC, minutes to Governing Body with specific issues escalated by the Quality Highlights Report | [5 empty] | Ongoing
the local based maternity plan includes increasing the choice of where to give birth from the current two oprions avaialble to the recommended three options (consultant led, home and midwifery led) | [11 empty] | Ongoing
Enhanced specialist smoking cessation support for women who smoke during pregnancy will be provided | [11 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
SYB ICS LMS positively assured Barnsleys response to the Ockenden report
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Consequence | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 9.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 9: DIGITAL AND TECHNOLOGY |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
1. Development of a system wide shared care record 2. Ensure the delivery of the GP IT Futures Model to: - Comply with mandatory core standards re: interoperability and cyber security - Ensure HSCN supports effective and fast connectivity - Support the identification of equipment that poses a threat to cyber security e.g. pre Windows 10 software - Support the implementation and roll out of the GPIT refresh of IT equipment - Support the wider use of digital technology as described within the Long Term Plan - Working closely with the SY&B digital and IT workstream to deliver the digital road map - Delivery of O365 across Barnsley - Support the transition of video and online consultation software as the Doctorlink contract ends - Support the delivery of the Digital Primary Care First projects - Support the development of the Digital Citizen project in collaboration across "place" - Support the GP practices with digitisation of the Lloyd George records when confirmed by NHSEI - Support the roll out of the corporate Wi-Fi solution - Support the resilience work at Hillder House with the servers and CCG corporate IT needs - Support the upgrade to utilise digital technology for telephony resilience across GP practices and Hillder House 3. Development of a Barnsley "place" Digital Strategy that reflects the "system" digital strategy and aligns with the emerging Eststes strategy |  |  |  |  | Highest quality governance |  |  | There is a risk that the key deliverables will not be achieved if the following threats to delivery are not appropriately managed and mitigated: - Lack of IT technical expertise locally for input into projects and programmes of work / lack of technical support to ensure deliverables are robust - Primary Care colleagues fatigued with the amount of IT work scheduled - Short timelines to deliver projects - Supplier and equipment delays - constructive and timely engagement by system partners to deliver a SCR by 20/21 - system wide strategic digital strategy and planning currently under-resourced with no dedicated Barnsley resource available to progress this work - Incomplete information available from NHS Futures regarding future work.
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
F3 - Develop the underpinning digital and data capability to support population-based approaches
Committees providing assurance |  |  | PCCC & SMT | Executive Lead |  |  | JB | Clinical Lead |  |  |  | JH
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 12 | [5 empty] | Rationale: Likelihood has been scored at 3 as transition to new provider has been successfully completed but will be kept under review. Consequence has been scored at 4 given the major impact on the CCG and the system if digital and It technology is not safeguarded and fully exploited.
Current | 3 | 4 | 12
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Barnsley IT Strategy Group | [5 empty] | Monthly meetings to review SCR progress and refresh Digitial Roadmap. Minutes to GB | [5 empty] | Ongoing
BBS IT Delivery Group and BBS Digital Strategy Group established | [5 empty] | Monthly meetings to review progress of the delivery of key projects and programmes. Updates to SMT, GB and PCCC | [5 empty] | Ongoing
GP IT and Corporate IT service commissioned from BBS IT Services, the successor to eMBED. The new shared service is now establishing working protocols. Shared staffing allows for technical and network experience to be available to the CCG. Additional staffing to be secured if Digital First EOIs are successful as bids include resource. | [5 empty] | CCG representatives attend the BBS IT Delivery Group and BBS Digital Strategy Group. KPIs and other performance monitoring data is provided and reviewed. Isses would be escalated to SMT in first instance. | [5 empty] | Ongoing
SYB has led a procurement leading to the identification of Doctorlink as the preferred local provider of online consultation services. Contact in place until Oct 2021 with another 2 year option. | [5 empty] | Every Barnsley practice has Doctorlink installed for use within their practice. | [5 empty] | Complete
Redcentric become the commissioned service to maintain HSCN | [5 empty] | Transition to new HSCN network now complete across the Barnsley CCG & primary care estate | [5 empty] | Complete
Gaps in assurance | [6 empty] | Positive assurances received
Governance process to be established for the IT groups eg link with the IT Strategy group and the CCG Operational Group
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 10.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 10: COMPLIANCE WITH STATUTORY AND REGULATORY REQUIREMENTS |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
• Delivery of all the CCG's statutory responsibilities • Deliver statutory financial duties & VFM • Improve quality of primary & secondary services (inc reductions in HCAI, ensuring providers implement learning from deaths, and reductions in medication errors); • Involve patients and public; • Promote Innovation; • Promote education, research, and training; • Meet requirements of the Equality Act; • Comply with mandatory guidance for managing conflicts of interest • Adhere to good governance standards. |  |  |  |  | Highest quality governance |  | ü | There is a risk that if the CCG fails to deliver its statutory duties, due to weaknesses in its corporate governance and control arrangements, it will result in legal, financial, and / or reputational risks to the CCG and its employees.
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
Committee Providing Assurance |  |  | Audit Committee | Executive Lead |  |  | RW | Lay / Clinical Leads |  |  |  | MG,JS,NBa, NBe, CM
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 2 | 5 | 10 | [5 empty] | Rationale: Likelihood is 'unlikely' as arrangements now well established. Consequence is catastrophic due to very significant quality, financial & reputational impact of failure.
Current | 2 | 5 | 10
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Overall: Constitution, Governance Handbook, Prime Financial Policies, and suite of corporate policies | [5 empty] | Audit Committee provides oversight, supported by internal & external audit reports & opinions, LCFS work etc | [5 empty] | Ongoing
Governing Body & Committee Structure underpinned by clear terms of ref and work plans | [5 empty] | GB members sit on Committees. All Committee minutes taken to GB and significant issues are escalated. Committees produce annual assurance reports for the GB. | [5 empty] | Ongoing
Management Structure - responsibilities clearly allocated to teams and individuals | [5 empty] | Management action monitored by regular senior management team meetings. SMT decisions with a financial consequence reported through F&PC. | [5 empty] | Ongoing
Finance: Budgetary control, contract monitoring & QIPP monitoring arrangements. Scheme of Delegation requires SMT approval for spending commitments <£100k and GB approval over this level. | [5 empty] | Financial Plan signed off by GB each year. Monthly finance report to FPC and GB; internal & external audit reviews and opinions; GB formally adopt annual report & accounts. | [5 empty] | Ongoing
Performance monitoring arrangements | [5 empty] | Integrated Performance Reports to FPC provides assurance across all NHS Constitution pledges. Summary reports to GB. | [5 empty] | Ongoing
Quality: comprehensive and well established arrangements in place to monitor, assure and improve the quality of all commissioned services including Clinical Quality Boards, Quality Assurance visits, benchmarking, Primary Care Quality Improvement Tool, outcomes from CQC inspections in both primary and secondary care, review of serious incidents and never events, complaints & compliments, review of FFT, nurse leads for safeguarding adults & children who represent the CCG on the local safeguarding boards. | [5 empty] | Reporting of all relevant information to the Quality & Patient Safety Committee, with assurance to Governing Body through Quality Highlights reports and sharing of minutes. | [5 empty] | Ongoing
Patient & Public Involvement: strategy in place, well established Patient Council and development of a local/regional citizen's panel, Healthwatch Barnsley holds independent role on engagement and equality committee and primary care commissioning committee, co-ordination of activity with partners, appropriate engagement & involvement re service changes, membership of consultation institute, active patient reference groups locally, funding provided to Barnsley Council to provide community engagement activity and to support a robust and sustainable thrid sector. | [5 empty] | Oversight by Equality & Engagement Committee. Assurance to Governing Body via minutes and bi-monthly PPI Summary reports. In previous years Internal Audit Reviews and NHSE assurance process also provided assurance re robustness of our arrangements. Compliance with statutory guidance on patient and public participation in commissioning health and care is assessed via the NHSE 'improvement and assessment framework'. (rated green in 2017/18, 2018/19 and 'Green Star' in 2018/19). | [5 empty] | Ongoing
Equality: EDS2 used to ensure compliance with PSED requirements; Equality Action Plan monitored vie E&D Group and E&E Committee; E&D Lead; E&D training provided to all staff; EQIA policy in place and EQIAs attached to GB papers where appropriate; Staff survey results considered & acted upon; HR policies approved & embedded. | [5 empty] | Progress monitored by Equality, Diversity & Inclusitivity Group and reported quarterly to Equality & Engagement Committee. Assurance to GB via E&E Committee Minutes and annual assurance report. Summary of key actions on CCG website each year. | [5 empty] | Ongoing
Conflicts of Interest: standards of business conduct policy in place & compliant with statutory guidance; registers of interests maintained & published; declared conflicts managed in meetings and / or during procurements; online training provided to key staff; oversight by Audit Committee; Conflicts of Interest Guardian in place; PCCC has delegated authority where GB cannot make decisions. | [5 empty] | Oversight by Audit Committee. Regular reports to GB. Declarations at every Committee and GB meeting. Annual IA review of arrangements. NHSE Quarterly self certification process. | [5 empty] | Ongoing
Information Governance: strategy & policies in place, SIRO / Caldicott Guardian identified, training provided for all staff, information asset register in place, committee report & business case template prompts consideration of IG issues. GDPR / compliant processes in place. DPO service provided by third party provider. | [5 empty] | DSP Toolkit (formerly IG Toolkit) compliance achieved every year. Reporting via IG Group==>QPSC==>GB. | [5 empty] | Ongoing
Risk Management: Risk management framework (GBAF and RR) provides assurance that risks have been identified and are being managed | [5 empty] | GBAF and Risk register updated monthly and considered at all Committees and meetings of the GB | [5 empty] | Ongoing
Health & Safety and Business Continuity Group established to oversee compliance with statutory Fire & Health & Safety & Business Continuity requirements | [5 empty] | Annual Report & update reports taken to Audit Committee. | [5 empty] | Ongoing
MAST: Statutory & Mandatory training programme in place for all staff, inc GB members, as well as IPR reviews, development sessions for Governing Body inc conflicts of interest, risk management & assurance etc | [5 empty] | L&D team provides dashboard which is considered by management team on a regular basis. | [5 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
The CCG received a 'Green Star' rating from NHSE in respect to compliance with statutory guidance on patient and public participation in the 2018/19 IAF ratings published in July 2019, and the 2019/20 ratings published in November 2020. The CCG received a 'significant assurance' opinion from Internal Audit following its review of the Governance & Risk Management arrangements (Sep 2019). The CCG received a 'significant assurance' opinion from internal audit on its conflicts of interest arrangements (Dec 2020). The CCG received a 'substantial assurance' opinion from internal audit on the Integrity of the General Ledger and Financial Reporting (Jan 2021). The CCG received a 'significant assurance' Head of Internal Audit Opinion at the conclusion of the 2020-21 Internal Audit programme (June 2021) The CCg received an unqualified opinion from KPMG on the CCG's Annual report & Accounts 2020-21 (June 2021)
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
RR 20/03 If the BCCG CHC team is unable to deliver its recovery plan to enable the backlog of reviews to be cleared and new cases to be processed in a timely way, with robust case management processes in place that demonstrate value for money whilst not compromising quality of care , there is a risk of adverse financial consequences for the CCG and inappropriate or out of date care packages being provided for patients which potentially would not be meeting their health needs. This could also have implications on meeting the KPI's as set by NHSE. | [6 empty] | For details of mitigating actions see Corporate Risk Register 20/03. Latest update (Jan-22) states: O/S reviews are at 7.5 % which maintains the good position of the service. The Team is on target to meet DOH for Q3, NHSE KPI met for December with 100% which is improvement from October and November 2021. Vacancy still present for LD nurse WTE B6 and two B6 WTE will be going on Maternity leave from February 2022. No change in position of PHB or capacity and demand work. No change in risk rating.
13/13 If improvement in Yorkshire Ambulance Service (YAS) performance against the ARP response time targets is not secured and sustained, there is a risk that the quality and safety of care for some patients could be adversely affected. | [6 empty] | For details of mitigating actions see corporate risk register 13/13. As at Jan-22 the risk rating remains red due to continued concerns about current levels of demand due to winter pressures and covid. Indeed the risk score was increased from by GB in January 2022 from 15 to 20 in light of the impact of these pressures on response times and the number of serious incidents. The position will be kept under close consideration by QPSC and the GB.
RR 14/15 Discharge medication risks related to poor or incomplete D1 discharge letters | [6 empty] | For details of mitigating actions see corporate risk register 14/15. latest update states: The BHNFT D1 working group has been put on hold until spring 2022 - due to the hospital prioritising COVID 19 backlog and expected winter system pressures. A designated shared BHNFT email address for Community Pharmacy (CP) DMS reconciliation queries has been set up and clinical pharmacists are being copied into emails. A DMS working group has been established to plan & develop DMS and discuss issues.
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Consequence | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Risk rating | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 11.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 11: DELIVERY OF ENHANCED HEALTH IN CARE HOMES |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
Delivery of all 17 elements and sub elements of the Barnsley Care Homes Delivery Plan. This includes the elements of the Enhanced Health in Care Homes (EHCH) Framework and the Covid-19 Pandemic specific support. 1. Engagement with care homes on all requisites of the delivery plan 2. EHCH Primary Care Network (PCN) Specification 3. Named Clinician for each care home 4. Coordinated health and social care MDT support 5. Specialist Support 6. Out of Hours support 7. Infection Prevention and Control (IPC) including Personal Protective Equipment (PPE) 8. Mutual Aid 9. Testing / Swabbing 10. Medicines 11. Equipment 12. Discharge to Assess (D2A) and Intermediate Care (IMC) 13. Secondary Care support 14. Personalised care 15. Workforce support 16. Technology 17. Integrated Care System link-in |  |  |  |  | Highest quality governance |  |  | There is a risk that the CCG will not be able to deliver the elements of the Care Homes Delivery Plan if the following issues are not mitigated: 1.Acuity of the Covid 19 need across Barnsley meaning that the more transformational elements of the plan will need to be shelved or slowed down. 2. Decrease in bed occupancy and risk to business viability and market sustainability 3. Financial pressures and priorities 4. CCG not having direct input and oversight of quality assurance monitoring and safeguarding in care homes 5. Best use of technology in care homes - variance types of technology used and in consistency of use 6. Potential IG issues in current methods of remote consultation using IT equipment 7. Insufficient staff/resource (Matrons, Clinical Pharmacists and some GP practices) to undertake delivery of MDTs in care homes. 8. Availability of essential equipment (e.g PPE) 9. Interdependencies with other work streams and potential for gaps in communication and escalation of issues
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
Committee Providing Assurance |  |  | Q&PSC | Executive Lead |  |  | JW | Clinical Lead |  |  |  | Dr J MacInnes
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 12 | [5 empty] | Likelihood assessed as 3 'possible' taking into account learning from Phase 1 responses, service delivery, issues and risks; discussions about the risk and issues in recovery phase; and emerging picture in new phase of the pandemic in light of pending Winter pressures. Consequence assessed as 4 'major' given potential impact on Barnsley patients if the deliverables are not achieved.
Current | 3 | 4 | 12
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
Delivery work plan and risk log in place | [5 empty] | Monitored and managed via a multi - agency Delivery Group and Bronze Discharge and Out of Hospital Group. Minutes and action logs available. Leads and co-leads in place with clear responsibility for delivery – supervision of leads within line management structures Escalation of risks and issues to Silver and other appropriate forums as required. Regular reporting to Quality and Patient Safety Committee Risk log updates as indicated by BRAG rating | [5 empty] | Ongoing
Barnsley Care Homes Plan is being reviewed alongside the role of the Care Home Delivery Group to ensure the plan supports recovery and ongoing improvement in the support to care homes, recognising the significant impacts of COVID19 | [5 empty] | Work being led by the CCG Chief Operating Officer and BMBC Head of Joint Commisisoning. Will feed into ICDG to agree priorities and future governance and delivery arrangements as part of place based arrangements. | [5 empty] | Ongoing
Gaps in assurance | [6 empty] | Positive assurances received
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Consequence | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Risk rating | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## 12.1
2022-03-03 | NHS Barnsley CCG Governing Body Assurance Framework 2021-22
PRIORITY AREA 12: DELIVERING THE COVID VACCINATION PROGRAMME & MEETING THE NEEDS OF PATIENTS WITH COVID-19 |  |  |  |  | Delivery supports these CCG objectives: |  |  | PRINCIPAL THREATS TO DELIVERY
• All adults to be offered a first dose of the vaccination by the end of July 2021 • Maximise uptake by engeging with local communities to increase vaccination uptake and reduce vaccine hesitancy • Work with partners to maximise capacity to deliver the vaccination programme through the mixed delivery model including GP/PCN sites, vaccination centres, hospital hubs and community Pharmacy • Support General Practice to deliver phase 2 of the vaccination programme for cohorts 10-12 (18 - 49 year olds) • Delivery of COVID 19 booster programme from Autumn • Support delivery of COVID 19 vaccination of Children - in line with guidance by JCVI • Delivery of home oximetry, post covid assessment and support for patients with 'Long COVID' |  |  |  |  | Highest quality governance |  |  | There is a risk that the CCG will not be able to deliver the covid vaccination programme and meet the needs of patients with covid-19 if the following issues are not mitigated: 1. Staffing capacity being sufficient to continue to deliver the vaccination programme, 2. Vaccination supply being insufficient to meet targets 3. Negative public attitudes and hesitancy towards the vaccination impact upon uptake rates 4. Engagement and support of all partners to maximise available capacity and uptake of the vaccine 5. Understanding of the number of 'Long COVID' patients and establishment of pathways to provide ongoing support
[5 empty] | High quality health care |  | ü
[5 empty] | Care closer to home |  | ü
[5 empty] | Safe & sustainable local services |  | ü
[5 empty] | Strong partnerships, effective use of £ |  | ü
Links to NHSE/I Planning Guidance
B - Delivering the covid vaccination programme and continuing to meet the needs of patients with covid-19
Committee Providing Assurance |  |  | TBC | Executive Lead |  |  | JW | Clinical Lead |  |  |  | TBC
Risk rating | Likelihood | Consequence | Total | [5 empty] | Date reviewed |  | 2022-02-01
Initial | 3 | 4 | 12 | [5 empty] | Likelihood currently judged to be 'possible' as there are many external factors such as supply and changes to vaccine that could impact particulalry on the delivery of the programme. Initial likelihood was likely but good progress has been made and early supply concerns have improved reducing the likelihood to possible. Consequence is judged as major due to the potential impact on both the health of the population and organisations reputation.
Current | 2 | 3 | 6
Appetite | 3 | 4 | 12
Approach | Tolerate
Key controls to mitigate threat: | [5 empty] | Sources of assurance | [5 empty] | Rec'd?
South Yorkshire and Bassetlaw COVID Vaccination Steering Board established providing oversight to the wider programme and ensuring arrangements for coordination across SYB including of vaccine allocations, addressing inequalities and ensuring appropriate mechanisms for delivery across Vaccination Centres, Hospital Hubs, General Practice and Community Pharmacy | [5 empty] | Monthly - Steering Board made up of partners from key sectors across SYB. Jointly Chaired by SRO for the Lead Provider (CE Sheffield Teaching Hospital) and SRO for the Primary Care Programme (AO Doncaster CCG) Representation is also included from PH and LA's to ensure wider support | [5 empty] | Ongoing
SYB Vaccine Delivery Group established to support coordination of delivery, ensure learning across SYB and maximise uptake across SYB. | [5 empty] | Weekly - Chaired by SRO for the Primary Care Programme, coordinates allocation of the vaccine supply within SYB to ensure equitable supply and progress across all areas. Workstreams include, delivery models, health inequalities, staffing, engagement, communications and data. | [5 empty] | Ongoing
Barnsley Vaccination Group in place, bringing together local partners across Primary, Community and Acute Care and the Local Authority to support delivery of the local delivery programme in Barnsley | [5 empty] | Weekly - Chaired by COO Barnsley CCG. All partners represented. Focus on partnership support, working together, developing delivery models, responding to changes to guidance or requirements in relation to vaccine usage etc. Successfully coordinated delivery of vaccination programme for H&SC workforce and phase 1 of the overall vaccination programme. | [5 empty] | Ongoing
Barnsley Vaccination Engagement Group in place, bringing together local partners across Primary, Community and Acute Care and the Local Authority to support engagement activities and development of plans to target vaccination delivery models to meet the needs of local communities and reduce inequality in uptake | [5 empty] | Weekly - Chaired by Service Director for Public Health, BMBC. Coordination of engagement activities and development of approaches including 'Make Every Contact Count' to maximise the reach of all teams across partners who have regular contact with local people and communities. Inequalities in uptake have been identified across different geographical communities and certain groups of the population and activity has been targetted to reacing these and maximising uptake. | [5 empty] | Ongoing
Contractual arrangements in place with General Practices to delivery phase 1, 2 and 3 of the vaccine programme working collectively as a single PCN Grouping | [5 empty] | All GP practices in Barnsley have signed up to delivery of the Vaccine Programme via the Enhanced Service. BHF is leading delivery of the programme on behalf of BP practices with the support of each practice in relation to delivery of local clinics in practice, workforce provision and inviting patients for vaccine/following up and recalling for 2nd dose. | [5 empty] | Ongoing
3 Primary Care Hub Sites in place from which to coordinate and deliver local vaccination on behalf of General Practice to Barnsley patients who are eligible for the vaccine | [5 empty] | Designated sites were approved by NHS England at Apollo Court, Dearne Valley Group Practice and Priory Campus. These Local Vaccination Service Hubs are managed by BHF on behalf of the Primary Care Network/GP practices. All local vacination activity is coordinated via the 3 designated sites. Roaving vaccination models in place to deliver to residential settings, vulnerable groups such as those who are homeless and to housebound patients Pop up clinics in GP practices have taken place to deliver vaccine to groups of patients who may not have been able to access the vaccine at a local designated site. A range of booking methods are in place to ensure everyone is able to be invited and acess a vaccine. This has included telephone calls, test messages, vaccine call centre and letter. All targets/expectations on uptake levels have been achieved with all over 50's offered a vaccine by mid April and the remainder of the adult population offered a first dose by the end of July 2021. Delivery has commenced to 16-17 year olds and eligible 12-15 and 5-11 year olds n line with JCVI guidelines | [5 empty] | Ongoing
Barnsley School Age Vaccination and Immunisation Service is leading the delivery of the school age vaccination programme for health 12 - 15 year olds. | [5 empty] | 1st visit to all secondary schools for 1st dose vaccination complete and schedule in place to revisit each secondary school in Barnsley to provide vaccination 91st and 2nd dose where eligible). Arrangements in place to vaccinate those who are home schooled or not attending school for other reasons. Arrangements in place to utilise local vaccination sites to offer vaccination to those not vaccinated in school. | [5 empty] | Ongoing
Long Covid pathways in place to support identification, assessment and treatment. | [5 empty] | Pathways established bringing together a partnership of local providers including BHF, BHNFT and SWYPFT and utilising current commissioned services to effectively support patients identified as having 'long COVID'. Additional investment is available to support expansion of services to meet the need of an increased number of patients | [5 empty] | In place
Gaps in control | [6 empty] | Actions being taken to address gaps in control / assurance
SCORE: | A | M | J | J | A | S | O | N | D | J | F | M
Likelihood | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Consequence | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Risk rating | 12 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Tolerance | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12